## Priority Summary
[6 empty] | 23.25% | 11.62% | 19.38% | 23.25% | 22.5%
PT Lead | Support | Tier | Land Owner | Project Name | Overall Project Score | Transactability Score | Env Score | IX Score | I&C Score | Redev Score | Notes on "0" Score | Initial Valuation | Stage Gate | Land Control | Number of Sites | Energy Market | Location | Site Acres | Base Case Technology | Base Case Capacity | Base Case COD | Objective | Next Key Milestones | Weekly Priority Tasks | Contextual Comments or Notes
RB | TBD | 0 | Talen | Dartmouth Power Associates LP | 0 | [7 empty] | P | Y | 1 | 81 | Dartmouth, MA | [25] |  | 1992 | Emily Kraus |  | Closed | 10/6/25: | Signed
pb | Ann | 0 | BPU | Quindaro (Thermal) | 3.65 | 4 | [6 empty] | 3 | Y | 1 | SPP | Kansas City, KS | 60 | Dual Fuel Recips | 150 | 2028 | Build and Operate Power Facility Under Long Term Offtake Agreement | Secure Offtake Agreement (1Q 2026) | - Finalize EPC Outreach - Kick off air permitting strategy work - Advance procurement strategy - Submit intake forms to gas suppliers | - Entered ERAS process on Oct 17 - This week we - - Met with KDHE on known spill issues; KDHE assured PT/BPU that they can work on our timeline - Outreach to EPCs and met with Kewitt - Advanced contracting with Daelim
pb | - | 0 | NorthStar | Yankee (BESS) | 3 | 2 | 3 | 3 | 4 | 3 |  |  | 3 | Y | 1 | ISONE | Vernon VT | 140 | BESS | 440 | 2029 | Build and Operate BESS Facility | LOI on Offtake (1H 2026) | - Receive and review Eversource Interconnection assessment on VT to MA 345kV potential - Advance commercial discussions (dependent on task 1) | - Met with Eversource to discuss potential MA offtake on 9/19. Eversource to conduct a assessment to determine feasibility and capacity on their 345kV line. Once project potential confirmed, parties to discuss commericial opportunity. Eversource has not responded to two subsequent emails.
RB | TBD | 1 | Talen | Camden Plant Holding LLC | 0 | [7 empty] | P | Y | 1 | 145 | Camden, NJ |  |  | 1992 | Emily Kraus |  | Closed | 10/6/25: | Signed
pb | Ann | 1 | BPU | Quindaro (Data Center) | 3.65 | 3 |  |  |  | 4 |  |  | 3 | Y | 1 | SPP | Kansas City, KS | 60 | Powered Land | 300 | 2026 (sale/lease) | Sale or lease of powered land to 3rd party data center developer | Market Site (10/31/2025) | - Finalize teaser video and landing page and circulate to interested buyers - Discuss terms with BPU on "priority load" opportunity [This is the $2m for queue position 1 on load] | - Advanced marketing materials with consultants incl video, teaser, letter, NDA to near final status
pb | Ann | 3 | BP | BP Sites | [8 empty] | 0 | N | 4 | WECC, MISO, SPP | OR, WA, MO, IL | TBD | Thermal/Powered Land | TBD | TBD | Idenitfy and capture thermal/powered land opportunities at BP brownfield sites | Finalize Project Concept (10/31/2025) | - Call with BP on brownfield sites to confirm alignment on 10/29 | - PT team (Jason, PB, and Ann) reviewed sites and engaged BP for key details on priority opportunities.
RB | Ann |  | Alliance | Massena | [8 empty] | 0 | N | 1 | NYISO | Massena, NY
RB | Ann |  | Alliance | Hilburn | [8 empty] | 0 | N | 1 | NYISO | Hillburn, NY
RB | Ann |  | Alliance | Shoemaker | [8 empty] | 0 | N | 1 | NYISO | Middletown, NY
rb | TBD |  | Bill Gross | Camelot (Thermal) | 2.55 | 2 | 3 | 3 | 4 | 1 |  |  | 1 | N | 1 | SERC | Kingsland, GA | 600 | Thermal | 150 | 1H 2029 | Build and operate thermal plant to support capacity needs in OREMC territory | - Execute JDA (week of 10/27) - Complete Stage Gate 1 | - Finalize and execute JDA - Progress offtake discussions w/ OREMC and Morgan Stanley - Progress thermal site search and initial site assessments | - PT team met w/ Bill Gross 10/16 to discuss progress; Bill Gross finalizing property title documentation and entity certificates (prep for execution of JDA); Supports plan to search for additional sites in OREMC territory for gas plant development
rb | TBD |  | Bill Gross | Camelot (Data Center) | 2.55 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | N | 1 | SERC | Kingsland, GA | 600 | Powered Land | 300 | 1H 2029 | Provide data center or other load-intensive customer w/ powered land solutions | - Execute JDA & Secure Site Control (week of 10/27) | - Finalize and execute JDA - No other priorities scheduled
rb | TBD |  | National Fuel | National Fuel Sites | [8 empty] | 0 | N | 20 | PJM, NYISO | OH, PA, NY | TBD | Thermal / Powered Land | TBD | TBD | Identify and capture thermal / powered land opportunities at National Fuel sites | Finalize Project Concept - Stage Gate 0 (by EOY) for Selected Sites | - Finalizing initial assessment of sites (20 total) to determine which opportunities PT wants to pursue for thermal / powered land development | - Introduction to National Fuel (9/26) - Controls 20 sites across PJM and NYISO w/ strategic gas supply advantages - Seeking partner for development of sites - Sent status update to National Fuel on 10/20
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
10/6/25:
|  |  | GE | Parlin | 0 | [9 empty] | 1 | 108.4
rob | Georgia |  | Massena | Total | [15 empty] | 450
rob | Georgia |  | Shoemaker
rob | Georgia |  | Hillburn
rb | Jim |  | BP Whiting
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to find info